# Keshav: Spring 2026 Semester Plan

| Week of | Primary objective | Checklist (done = ☑) | Deliverable (end of week) | Dependencies / notes |
| --- | --- | --- | --- | --- |
| Jan 12, 2026 | Sync on equations + data requirements; define code interfaces | ☐ Review governing flux/transport equations & parameter list ☐ Freeze data schema (units, species naming, time stamps, stage IDs) for DATA3 ☐ Map datasets to use-cases: single-salt (KCl/NaCl/CaCl2/LaCl3), two-salt, prospective 3-salt | One-page interface/spec (schema + pipeline stages) + dataset inventory | Align with Laurianne/Jonathan/Molly equation-derivation review (Jan–Feb milestone) |
| Jan 19, 2026 | Implement data configuration layer (schema + validators) | ☐ Create configuration objects (experiment metadata, components, calibration curves) ☐ Add validators (missingness, monotonic time, unit consistency, species presence) ☐ Write minimal unit tests on a small KCl dataset slice ☐ Document config conventions in README | Config module merged + tests passing on KCl | Use shared naming conventions for salts/species across DATA3 |
| Feb 02, 2026 | Bring DATA framework up to date; single-salt end-to-end run | ☐ Integrate multicomponent calibration-curve support into ingestion ☐ Run end-to-end pipeline on KCl and at least one of NaCl/CaCl2/LaCl3 ☐ Add plotting hooks for sanity checks (mass balance, permeate trends) ☐ Log numerical settings for reproducibility (scaling, tolerances) | Reproducible single-salt ParmEst run + sanity-check plots – legacy style | Matches Laurianne Goal #1 Jan–Feb: bring DATA up to date; test on single salts |
| Feb 09, 2026 | General solute flux equations integrated + validation sweep | ☐ Make a list of all the equations used from Data I and II ☐ Implement/verify generalized solute flux equation(s) in model layer ☐ Run tests for experiment data files run using .MAT (published experiments) and .XLSX files | Single-salt process model report (what works, what breaks, why) | Coordinate with Dowling group expectations for DATA3 |
| Feb 16, 2026 | Robust processing: filtering, interpolation, and uncertainty handling | ☐ Standardize smoothing/interpolation rules ☐ Add measurement-uncertainty plumbing (weights/covariance placeholders) ☐ Add regression diagnostics (residuals vs time, leverage) ☐ Decide default pre-processing for manuscript reproducibility | Processing defaults + diagnostics plots template | Avoid overfitting preprocessing; keep toggles for sensitivity analysis |
| Feb 23, 2026 | Sensitivity + Fisher Information (FIM) integration for single-salt baseline | ☐ Compute scaled sensitivities for key parameters ☐ Compute FIM and conditioning metrics (eigenvalues, collinearity) ☐ Add automatic warnings for near-singularity / non-identifiability ☐ Package results into a consistent export (CSV/JSON) | Baseline FIM/identifiability module + example notebook | Sets up March two-salt AIC/model selection + 3-salt design criteria |
| Mar 02, 2026 | Two-salt pipeline readiness (model variants + AIC harness) | ☐ Implement model-variant runner (different transport hypotheses) ☐ Add AIC computation (and AICc if sample-size is small) ☐ Verify consistent likelihood definition across datasets ☐ Dry-run on a synthetic two-salt dataset or subset | Automated model-selection harness (AIC) ready for real two-salt data | Matches Laurianne Goal #1 Mar–Apr: compile model selection results using AIC |
| Mar 09, 2026 | Two-salt analyses round 1 (DATA framework) | ☐ Run two-salt datasets through full pipeline ☐ Generate AIC tables across model variants ☐ Identify systematic misfits (which component, which regime) ☐ Draft figure candidates (AIC bar/heatmaps, residual panels) | Two-salt model-selection results v1 + initial figure set | Share early results so Laurianne can begin outlining manuscript/figures |
| Mar 16, 2026 | Two-salt analyses round 2 + robustness | ☐ Repeat with alternate weighting / preprocessing toggles ☐ Check parameter stability across initial conditions / subsets ☐ Document sensitivity of AIC rankings to assumptions ☐ Propose shortlist of credible models for 3-salt planning | Robustness memo + recommended model shortlist | Feeds Laurianne/Jonathan back-of-the-envelope calculations (Mar–Apr) |
| Mar 23, 2026 | 3-salt experiment design criteria (MBDoE-oriented) | ☐ Define candidate design variables (feed composition, pressure, stages, time horizon) ☐ Compute expected information metrics for candidate designs (FIM-based) ☐ Identify designs that discriminate top models (D-opt / E-opt / ΔAIC proxies) ☐ Summarize practical constraints and apparatus needs | 3-salt design recommendation (ranked conditions + rationale) | Align with ‘Identify conditions for a 3-salt experiment; apparatus status?’ |
| Mar 30, 2026 | Manuscript integration support (methods + SI scaffolding) | ☐ Write method notes for pipeline: schema → processing → ParmEst → AIC → MBDoE ☐ Organize code outputs for figures (naming, scripts, provenance) ☐ Draft SI outline: equations, assumptions, identifiability, numerical settings ☐ Create ‘reproduce figure’ scripts for at least 2 key figures | Reproducibility bundle (scripts + SI outline) | Keeps writing synchronized with evolving results; reduces last-minute crunch |
| Apr 06, 2026 | Close March: finalize two-salt story + handoff for experimentation | ☐ Finalize AIC tables/plots (publication quality) ☐ Document model-selection story (what changes with salt combinations) ☐ Deliver 3-salt design packet to Laurianne ☐ Create issue list for remaining code gaps | Two-salt results package + 3-salt design packet + prioritized backlog | Supports Laurianne’s Mar–Apr manuscript outline + 3-salt planning |
| Apr 13, 2026 | Code hardening + end-to-end regression testing | ☐ Add regression tests for single-salt and two-salt pipelines ☐ Add versioned outputs (hashes/metadata) for reproducibility ☐ Refactor for clarity (no math changes) + docstrings ☐ Confirm ParmEst convergence robustness | Stable internal code tag + regression test suite | Prevents figure drift during manuscript iterations |
| Tentative | Finalize MBDoE/identifiability narrative + figure polish | ☐ Polish identifiability/FIM plots and captions ☐ Write limitations bullets (non-identifiability, tradeoffs) ☐ Ensure consistent notation with Laurianne’s derivations ☐ Prepare slide-ready one-page summary figure | Final MBDoE/identifiability figure set + narrative bullets | Addresses “method/equations clarity over results” feedback |
| Tentative | Manuscript support sprint (results-to-text alignment) | ☐ Cross-check figure claims vs computed outputs (no leaps) ☐ Create a numbers table (key parameters + uncertainties) ☐ Provide AIC + MBDoE tables in manuscript-ready format ☐ Resolve remaining blocking questions internally | Manuscript-ready tables + checked-claims log | Keeps storyline defensible under skeptical review |
| Tentative | Pre-3-salt readiness: ingestion templates + analysis scripts | ☐ Prepare 3-salt data template (file structure + metadata expectations) ☐ Automate calibration-curve ingestion for new species mixes ☐ Add ‘new experiment quickstart’ guide ☐ Set up batch-run scripts for rapid turnaround when data arrives | 3-salt-ready analysis template + quickstart documentation | De-risks May–Summer analysis crunch |
| Tentative | May transition: 3-salt analysis pipeline dry-run + figure backlog closure | ☐ Run a dry-run on synthetic/placeholder 3-salt dataset ☐ Finalize any remaining figure scripts requested by Laurianne ☐ Write handoff notes for summer continuity (when new data arrives) ☐ Archive reproducible outputs (versioned) | 3-salt dry-run report + summer handoff notes + archived outputs | Matches Laurianne Goal #1 May–Summer: analyze 3-salt + continue figures |